## BOE3 Pivot (hidden)
BOE | BOE Start | BOE End | Task ID | Task Start | Task End | Total Hours | Resource | Performing Org | Start Date | End Date | Spread Curve | % Spread | Hours Spread
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 111, task 1 | 4/2011 | 12/2011 | 2000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[6 empty] | (blank) | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 50 | 1000
[7 empty] | 1CE2 | 4N64 | 4/2011 | 12/2011 | Curve 2 | 50 | 1000
|  |  | 222, task 2 | 4/2011 | 12/2011 | 3000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[6 empty] | (blank) | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 3 | 50 | 1500
[7 empty] | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 50 | 1500
|  |  | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 | 4000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[6 empty] | (blank) | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
[7 empty] | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 25 | 1000
[7 empty] | 1CE3 | 4N64 | 4/2011 | 12/2011 | Curve 4 | 25 | 1000
[7 empty] | 1CE4 | 6500 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
|  |  | 002, task 2 | 4/2011 | 12/2011 | 2000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[6 empty] | (blank) | 1CE1 | 4N64 | 4/2011 | 12/2011 | Curve 1 | 100 | 2000
|  |  | 222, task 2 | 4/2011 | 12/2011 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)

## BOEs (3) (hidden)
BOE | BOE Start | BOE End | Task ID | Task Start | Task End | Total Hours | Resource | Performing Org | Start Date | End Date | Spread Curve | % Spread | Hours Spread
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 111, task 1 | 4/2011 | 12/2011 | 2000
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 111, task 1 | 4/2011 | 12/2011 |  | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 50 | 1000
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 111, task 1 | 4/2011 | 12/2011 |  | 1CE2 | 4N64 | 4/2011 | 12/2011 | Curve 2 | 50 | 1000
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 222, task 2 | 4/2011 | 12/2011 | 3000
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 222, task 2 | 4/2011 | 12/2011 |  | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 3 | 50 | 1500
1 WBS 1, 01 CLIN 1 | 4/2011 | 12/2011 | 222, task 2 | 4/2011 | 12/2011 |  | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 50 | 1500
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 222, task 2 | 4/2011 | 12/2011
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 | 4000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 |  | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 |  | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 25 | 1000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 |  | 1CE3 | 4N64 | 4/2011 | 12/2011 | Curve 4 | 25 | 1000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 001, task 1 | 4/2011 | 12/2011 |  | 1CE4 | 6500 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 002, task 2 | 4/2011 | 12/2011 | 2000
2 WBS 2, 01 CLIN 2 | 4/2011 | 12/2011 | 002, task 2 | 4/2011 | 12/2011 |  | 1CE1 | 4N64 | 4/2011 | 12/2011 | Curve 1 | 100 | 2000

## BOE2 Pivot (hidden)
Type | WBS # | WBS Title | CLIN # | CLIN Title | BOE Start | BOE End | Task ID
BOE | 1 | WBS 1 | 01 | CLIN 1 | 4/2011 | 12/2011 | (blank)
| 2 | WBS 2
Labor Type | 1 | WBS 1 | 01 | CLIN 1 | 4/2011 | 12/2011 | 111
222
| 2 | WBS 2
Task | 1 | WBS 1 | 01 | CLIN 1 | 4/2011 | 12/2011 | 111
222
| 2 | WBS 2

## Sheet7 (hidden)
BOE ID | Type | WBS # | WBS Title | CLIN # | CLIN Title | BOE Start | BOE End | Task ID | Task Title | Task Start | Task End | Total Hours | Resource | Performing Org | Start Date | End Date | Spread Curve | % Spread | Hours Spread
1 | BOE | 1 | WBS 1 | 01 | CLIN 1 | 4/2011 | 12/2011 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
| Task | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | 111 | task 1 | 4/2011 | 12/2011 | 2000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[8 empty] | 222 | task 2 | 4/2011 | 12/2011 | 3000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
| Labor Type | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 50 | 1000
[17 empty] | Curve 3 | 50 | 1500
[13 empty] | 1CE2 | 4N64 | 4/2011 | 12/2011 | Curve 2 | 50 | 1000
[14 empty] | 5600 | 4/2011 | 12/2011 | Curve 2 | 50 | 1500
2 | BOE | 2 | WBS 2 | 02 | CLIN 2 | 4/2011 | 12/2011 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
| Task | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | 001 | task 1 | 4/2011 | 12/2011 | 4000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
[8 empty] | 002 | task 2 | 4/2011 | 12/2011 | 2000 | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank)
| Labor Type | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | (blank) | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
[14 empty] | 4N64 | 4/2011 | 12/2011 | Curve 1 | 100 | 2000
[13 empty] | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 25 | 1000
[13 empty] | 1CE3 | 4N64 | 4/2011 | 12/2011 | Curve 4 | 25 | 1000
[13 empty] | 1CE4 | 6500 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000

## BOEs (2) (hidden)
BOE ID | Type | WBS # | WBS Title | CLIN # | CLIN Title | BOE Start | BOE End | Task ID | Task Title | Task Start | Task End | Total Hours | Resource | Performing Org | Start Date | End Date | Spread Curve | % Spread | Hours Spread
1 | BOE | 1 | WBS 1 | 01 | CLIN 1 | 4/2011 | 12/2011
1 | Task | [6 empty] | 111 | task 1 | 4/2011 | 12/2011 | 2000
1 | Labor Type | [11 empty] | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 50 | 1000
1 | Labor Type | [11 empty] | 1CE2 | 4N64 | 4/2011 | 12/2011 | Curve 2 | 50 | 1000
1 | Task | [6 empty] | 222 | task 2 | 4/2011 | 12/2011 | 3000
1 | Labor Type | [11 empty] | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 3 | 50 | 1500
1 | Labor Type | [11 empty] | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 50 | 1500
2 | BOE | 2 | WBS 2 | 02 | CLIN 2 | 4/2011 | 12/2011
2 | Task | [6 empty] | 001 | task 1 | 4/2011 | 12/2011 | 4000
2 | Labor Type | [11 empty] | 1CE1 | 4F53 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
2 | Labor Type | [11 empty] | 1CE2 | 5600 | 4/2011 | 12/2011 | Curve 2 | 25 | 1000
2 | Labor Type | [11 empty] | 1CE3 | 4N64 | 4/2011 | 12/2011 | Curve 4 | 25 | 1000
2 | Labor Type | [11 empty] | 1CE4 | 6500 | 4/2011 | 12/2011 | Curve 1 | 25 | 1000
2 | Task | [6 empty] | 002 | task 2 | 4/2011 | 12/2011 | 2000
2 | Labor Type | [11 empty] | 1CE1 | 4N64 | 4/2011 | 12/2011 | Curve 1 | 100 | 2000

## BOE & Resource Combo
BOE ID | BOE Title | Type | Task ID | Task Title | MOQ Equation | MOQ Type | MOQ Rationale | Segment Region | WBS # | WBS Title | Multi WBS/CLIN | CLIN # | CLIN Title | BOE Start | BOE End | BOE Custom Field | Total BOE Hours | Total BOE Cost | Material BOE | Task Description | Historical Metrics | Task Start | Task End | Task Custom Field | Total Task Hours | Total Task Cost | Element Of Cost | Resource Description | Resource Type | Resource Code | BRC | BRC Description | BRC Type | BRC Segment Region | Performing Org | Perf Org Description | Spread Curve | % Spread | Hours Spread | Cost Spread | Resource Custom Field | Year | Month | Hours | Cost

## BOEs
BOE ID | BOE Title | Type | WBS # | WBS Title | CLIN # | CLIN Title | BOE Start | BOE End | BOE Custom Field | Total BOE Hours | Total BOE Cost | Multi WBS/CLIN | Material BOE | Task ID | Task Title | Task Description | MOQ Equation | MOQ Type | MOQ Rationale | Historical Metrics | Task Start | Task End | Task Custom Field | Total Task Hours | Total Task Cost | Element Of Cost | Resource Description | Region/Segment | Resource Type | Resource Code | BRC | BRC Description | BRC Type | BRC Segment Region | Performing Org | Perf Org Description | Travel Mode | Departure loc | Destination | Start Date | End Date | Spread Curve | % Spread | Hours Spread | Cost Spread | Resource Custom Field
Note on O1: If a Task ID does not exist, one will automatically be generated for it in this Export file.

## BOE Status
WBS # | WBS Title | BOE Title | CLIN # | CLIN Title | Start Date | End Date | Total Hours | Total Cost | Authors | Approvers | Status | Multi WBS/CLIN | Material

## Resource Spreads
Task ID | Task Title | MOQ Type | WBS Title | WBS # | CLIN # | CLIN Title | Segment Region | Resource Type | BRC Type | BRC Segment Region | Performing Org | Year | Month | Hours | Cost

## MOQ by BOE by Task
BOE ID | BOE Title | Task ID | Task Title | MOQ Equation | MOQ Type

## MOQ Table Data
BOE ID | BOE Title | Task ID | Task Title | MOQ Type | Table Name | Repository Name | Query Type (Weekly/Monthly) | Date of Report | Historical Program Name | WBS/WBS Element | Period of Performance (PoP): Start Date | Period of Performance (PoP): End Date | Employee ID Filters | Total Relevant Hours After Employee ID Filters Applied | MOQ Table Custom Field

## WBS
genBOE WBS ID | WBS # | WBS Title | CLINs | Design Element
Note on A1: Do not change the genBOE WBS IDs. The genBOE WBS IDs in column A are unique identifiers for WBS elements. One will be automatically generated for each new WBS element once the import is complete. By default, this column is hidden to prevent accidental edits.
Note on B1: Used to define a WBS in the Workspace. Each WBS # can have up to 10 levels with 5 characters for a level but it cannot be more than 30 characters. Use a period to separate each level. Example: 1.1
Note on C1: Each WBS Title can have up to 100 characters.
Note on D1: Indicate the CLINs associated with this WBS CLINs must exist on the Manage CLINs page in order to associate a CLIN to a WBS. Enter only the CLIN #. Separate multiple CLINs with a comma. Example: 0001, 0002, 0003

## User Permissions
genBOE User ID | AD Group | User | Workspace Administrator | Author | Subcontractor Author | Reviewer | Approver | Subcontractor Admin

## CLINs
genBOE CLIN ID | CLIN # | CLIN Title | Start Date | End Date | Contract Type
Note on A1: Do not change the genBOE CLIN IDs. The genBOE CLIN IDs in column A are unique identifiers for CLINs. One will be automatically generated for each new CLIN once the import is complete. By default, this column is hidden to prevent accidental edits.
Note on B1: Used to define a CLIN in the Workspace. Each CLIN # can have up to 20 characters.
Note on C1: Each CLIN Title can have up to 100 characters.
Note on D1: Indicate the Start Date of the CLIN. Start Date should be in the following format: m/yyyy or mm/yyyy. Start Date must be on or after the Contract Start Date.
Note on E1: Indicate the End Date of the CLIN. End Date should be in the following format: m/yyyy or mm/yyyy. End Date must be on or after the Contract Start Date.

## Workspace Identification
Workspace/Proposal Name
Description
Line Of Business
Proposal Class
Contract Type
Estimating Lead/Pricer
Contract Start Date
Contract End Date
Proposal Submittal Date
Resource Decimal Precision
Cost Decimal Precision
Tracking #
Is Using Equivalent Person (EP)
OCI
Proposal Status
Proposal Comments
SAP Connection Enabled